## Cover
Requirements Suite
Requirements Definition ¦ Functional Requirements — REQ-ID ↔ FUN-ID linked
Project Name | AI-Assisted Procurement Decision Support — Phase 1: ONE Excel Automation
BA / Author | 【氏名】
PM | 【氏名】
Version | 1.1
Created | 2026-06-29
Doc # | PROC-AI-P1-REQ
Status | Draft
Sheet Structure
How-to Guide | Column explanations, rules, cross-reference guide
Requirements List | REQ-IDs — high-level requirements signed by stakeholder
Functional Requirements | FUN-IDs — detailed functions linked to REQ-IDs
Traceability Matrix | Auto cross-reference: REQ-ID ↔ FUN-ID ↔ WBS Task ID (auto-formula)
AI Prompt | Copy-paste AI generation prompt
Sheet Protection | Protected sheets are locked to prevent accidental edits. Password: THIRDWAVE2026 To edit: Review tab → Unprotect Sheet → enter password → edit → re-protect when done.

## How-to Guide
AI-HEAVY TRACK: If using the AI-Heavy template, all requirements are PROVISIONAL until Gate 2 (Quality Rubric signed by stakeholder). Mark Status = Draft (Provisional) until then. Requirements are baselined only after Gate 2.
How-to Guide — Requirements Suite (Waterfall)
Purpose
REQ-ID Rules
| FUN-ID Rules | Sequential: FUN-001, FUN-002… Each FUN must link to a REQ-ID in col C. Col C (Linked REQ-ID) drives the Traceability Matrix auto-formula — always fill it. Scale: Estimated Effort in person-days (e.g. 2, 5, 10, 20). | Required
| Linked Task Ref (WF: WBS Task ID) | WF projects: Enter the WBS Task ID from the Project Plan (e.g. WBS-1.1.1, WBS-1.2.3). This links requirements and functions directly to the project schedule. WSF projects: Use PBI-ID (e.g. PBI-001) — assigned during Sprint Planning. AI-Heavy projects: Requirements are PROVISIONAL until Gate 2. Mark all rows as 'Draft (Provisional)' in the Status column until the Quality Rubric is signed. Do not reference PBI-IDs or WBS task IDs before Gate 2 — capability is still being proven. | See note
| Acceptance Criteria | Write in Given / When / Then format. RULE: AC must only describe HOW to verify an existing requirement. NEVER introduce new functionality in AC — add a new REQ row instead. Detailed test steps belong in the Test Plan document (not here). | See note
| Status — Requirements List | Tracks APPROVAL lifecycle of the requirement itself: Draft → Under Review → Approved → On Hold / Rejected NOT implementation progress — that belongs on Functional Requirements sheet. | See note
| Status — Functional Requirements | Tracks IMPLEMENTATION lifecycle of the function: Not Started → In Progress → Done / On Hold This is separate from requirement approval status. | See note
| Traceability Matrix (auto-formula) | Cols C & D use _xlfn.TEXTJOIN+IF array formulas. When you add a FUN row and set its REQ-ID in col C, the matrix automatically shows the FUN-ID and Function Name. DO NOT manually edit cols C, D, or H in the Traceability Matrix — they are auto-generated. Only col I (Notes) is editable in that sheet. | See note
| Sheet Protection | Key sheets are protected with password: THIRDWAVE2026 To edit: Review tab → Unprotect Sheet → enter password → edit → re-protect when done. Auto-formula cells in the Traceability Matrix are locked even when unprotected. | See note

## Requirements List
Requirements List
SINGLE SOURCE OF TRUTH · Enter REQ-IDs here. Link FUN-IDs via Functional Requirements sheet col C. WF: Use WBS Task IDs in col K. Status = approval lifecycle: Draft → Under Review → Approved.
REQ-ID (Required) | Category (Required) | Requirement Name (Required) | Requirement Detail (The system shall…) | Priority (MoSCoW) | UI / UX / Logic | Functional / Non-functional | Req Level | Linked FUN-ID (→ Traceability Matrix) | Linked Task Ref (WF: WBS Task ID ¦ WSF: PBI-ID) | Acceptance Criteria (Req-level: Given/When/Then) → Detailed test steps: Test Plan | Status (Approval lifecycle) | Remarks | Test Doc Ref (→ Test Cases & Test Plan)
REQ-001 | Data Ingestion | Auto NAS Ingestion | The system shall automatically read the 17 sub-files and 2 master files from the NAS daily, read-only. | Must | Logic | Functional | Detailed | FUN-001, FUN-002 | — | Given the source files exist on the NAS, When the daily refresh runs, Then all 17 sub-files + 2 masters are read read-only and a snapshot is recorded. | Under Review | Foundation
REQ-002 | Data | Parsing & Normalization | The system shall parse 部品詳細 and 購買計画 across heterogeneous layouts (.xlsb/.xlsx, non-standard files) by auto-detecting columns. | Must | Logic | Functional | Detailed | FUN-003, FUN-004 | — | Given mixed .xlsb/.xlsx layouts incl. FAN/Case_梱包, When parsing runs, Then 部品詳細 and 購買計画 are extracted with correct columns for every file. | Under Review | Foundation
REQ-003 | Functional | Inventory Consolidation | The system shall consolidate all SKUs into one table with stock balance, days-of-stock and excess/shortage/negative flags. | Must | Logic | Functional | Detailed | FUN-005, FUN-006 | — | Given parsed data, When consolidation runs, Then every SKU appears once with balance, days-of-stock and excess/shortage/negative flags. | Under Review | —
REQ-004 | Quality | Accuracy Gate | The system shall reconcile parsed records against expected counts per file and report PASS/WARN/FAIL each run. | Must | Logic | Functional | Detailed | FUN-007 | — | Given a consolidation run, When the gate runs, Then each file reports PASS/WARN/FAIL and total parsed equals expected (534/534). | Under Review | —
REQ-005 | Functional | Master History Aggregation | The system shall reproduce the master 部品予測 history by aggregating sub-file production data, and display existing forecast values without computing forecasts. | Should | Logic | Functional | Detailed | FUN-008 | — | Given sub-file production data, When aggregated into 部品予測 format, Then recent/active history matches the real master (100%) and forecast cells show existing values (no computation). | Under Review | —
REQ-006 | Quality | Data-Entry Error / Anomaly Detection | The system shall detect data-entry errors and anomalies (negative stock, aggregate rows, outliers) and track new vs fixed across scans. | Must | Logic | Functional | Detailed | FUN-009, FUN-010 | — | Given consolidated data, When a scan runs, Then negative-stock/aggregate/outlier issues are listed with explanations and new-vs-fixed counts vs the prior scan. | Under Review | Survey top (4.5)
REQ-007 | Functional | Overdue PO Detection | The system shall detect placed purchase orders past their delivery date and not yet received (actionable window). | Should | Logic | Functional | Detailed | FUN-011 | — | Given 購買計画 with delivery dates, When detection runs, Then open orders with PO#+supplier past delivery within 180 days are listed by days overdue. | Under Review | Survey 4.0
REQ-008 | Functional | Price & Supplier History | The system shall provide latest price and supplier history per SKU from 購買計画. | Should | UI | Functional | Detailed | FUN-012 | — | Given 購買計画 price/supplier data, When a user searches a SKU, Then its latest price, supplier and order history are shown. | Under Review | Survey 4.3
REQ-009 | Functional | Incoming-Stock Excess Warning | The system shall warn when scheduled inbound would push a SKU past its excess-days threshold. | Must | Logic | Functional | Detailed | FUN-013 | — | Given current stock and scheduled inbound, When projection runs, Then SKUs whose projected post-inbound days exceed the category excess threshold are warned. | Under Review | Survey 4.5
REQ-010 | Functional | Bilingual Dashboard & Export | The system shall present a bilingual (JA/EN) dashboard with one-click refresh and Excel export. | Must | UX | Functional | Detailed | FUN-014, FUN-015, FUN-016, FUN-017 | — | Given a completed refresh, When a user opens the portal, Then KPIs and all tabs render in JA/EN, ‘refresh all’ works, and Excel export produces the workbook. | Under Review | Survey 4.3
REQ-011 | Maintainability | Master Protection & DB-Ready | The system shall never modify the authoritative master and shall externalize source/layout config for a future Oracle DB swap. | Must | Logic | Non-functional | Detailed | FUN-018 | — | Given any run, When sources are read, Then no source/master file is modified and source/layout config is external. | Under Review | —

## Functional Requirements
Functional Requirements
LINK RULE: Every FUN-ID must reference a REQ-ID in col C — this drives the Traceability Matrix auto-formula. WF: Use WBS Task IDs in col I. Status = IMPLEMENTATION lifecycle (Not Started → In Progress → Done).
FUN-ID (Required) | Linked REQ-ID (Required → drives matrix) | Function Name (Required) | Function Detail (Required) | Priority (MoSCoW) | UI / UX / Logic | Scale (S/M/L/XL) | Linked Task Ref (WF: WBS Task ID ¦ WSF: PBI-ID) | Implementation Status | Remarks
FUN-001 | REQ-001 | NAS Daily Fetch | Scheduled read-only pull of 17 sub-files + 2 masters from the NAS share; snapshot each pull. | Must | Logic | M | — | In Progress
FUN-002 | REQ-001 | Configurable Source Path | Source folder switchable (local ↔ NAS) via one setting. | Must | Logic | S | — | Done
FUN-003 | REQ-002 | 部品詳細 Multi-layout Parser | Parse 部品詳細 across all 17 layouts incl. FAN / Case_梱包; both .xlsb and .xlsx. | Must | Logic | M | — | Done
FUN-004 | REQ-002 | 購買計画 Header Auto-detect | Parse 購買計画 by detecting columns from the header row (数量/価格/納品日/IO/綽名/仕入先/発注番号). | Must | Logic | M | — | Done
FUN-005 | REQ-003 | Unified SKU Table | Build one inventory table (balance, days of stock) keyed by 綽名. | Must | Logic | M | — | Done
FUN-006 | REQ-003 | Status Flags | Flag excess / shortage / negative-stock per SKU. | Must | Logic | S | — | Done
FUN-007 | REQ-004 | Reconciliation Gate | Three-way check (blocks vs parsed vs expected) → PASS/WARN/FAIL per file. | Must | Logic | M | — | Done
FUN-008 | REQ-005 | Forecast History Aggregation | Aggregate sub-file 生産予測 into 部品予測 format; validate vs master; display existing forecast. | Must | Logic | L | — | Done
FUN-009 | REQ-006 | Anomaly Rules | Rule-based detection: negative stock, aggregate rows, isolated outliers (explainable). | Must | Logic | M | — | Done
FUN-010 | REQ-006 | Anomaly History / Diff | Persist findings; compute new vs fixed each scan with a run history. | Must | Logic | M | — | Done
FUN-011 | REQ-007 | Overdue PO Detection | Open PO with PO# + supplier, delivery passed within the actionable window (180 days). | Should | Logic | S | — | Done
FUN-012 | REQ-008 | Price / Supplier History | Latest price/supplier + order history per SKU; searchable. | Should | UI | M | — | Done
FUN-013 | REQ-009 | Incoming-Excess Projection | Project days-after-inbound vs the category excess threshold; warn when exceeded. | Must | Logic | M | — | Done
FUN-014 | REQ-010 | KPI Dashboard & Tabs | KPI cards + tabs: summary, list, reconciliation, anomalies, procurement, master. | Must | UX | L | — | Done
FUN-015 | REQ-010 | Filter / Search / Sort | Category filter, status chips, SKU search, sortable tables. | Must | UI | M | — | Done
FUN-016 | REQ-010 | One-click Refresh All | Single action re-reads NAS and rebuilds consolidation + anomalies + procurement. | Must | UI | S | — | Done
FUN-017 | REQ-010 | Excel Export | Export consolidated + master-format workbook incl. reconciliation. | Must | UI | M | — | Done
FUN-018 | REQ-011 | Read-only Source Guard & Config | Open all source files read-only; per-file layouts in external config. | Must | Logic | S | — | Done
[7 empty] | WBS-1.3.3 | Not Started

## Traceability Matrix
Traceability Matrix — Auto-generated: REQ-ID ↔ FUN-ID ↔ UC-ID ↔ BR-ID
AUTO-FORMULA · Cols C & D use _xlfn.TEXTJOIN+IF array formulas scanning Functional Requirements col C. Add/change a FUN row → matrix updates automatically. Coverage recalculates automatically. Do NOT edit cols C, D, or H manually.
REQ-ID | Requirement Name | Linked FUN-IDs (auto-formula — do not edit) | Function Names (auto-formula — do not edit) | Linked Task Refs (WF: WBS IDs ¦ WSF: PBI-IDs) | Use Cases (UC-IDs) | Business Rules (BR-IDs) | Coverage (auto — do not edit) | Notes
REQ-001 | Auto NAS Ingestion |  |  | Phase 2/4 | UC-005 | —
REQ-002 | Parsing & Normalization |  |  | Phase 2 | — | —
REQ-003 | Inventory Consolidation |  |  | Phase 2 | UC-001 | BR-001, BR-002
REQ-004 | Accuracy Gate |  |  | Phase 2 | — | BR-003
REQ-005 | Master History Aggregation |  |  | Phase 3 | — | —
REQ-006 | Anomaly Detection + History |  |  | Phase 3 | UC-002 | BR-002
REQ-007 | Overdue PO Detection | — | Non-functional — see Non_Functional_Requirements.xlsx | Phase 3 | UC-003 | BR-004 | NFR Only
REQ-008 | Price & Supplier History |  |  | Phase 3 | UC-004 | —
REQ-009 | Incoming-Stock Excess Warning |  |  | Phase 3 | — | BR-005
REQ-010 | Bilingual Dashboard & Export |  |  | Phase 3 | UC-001 | —
REQ-011 | Master Protection & DB-Ready |  |  | Phase 2/3 | — | BR-006

## AI Prompt
AI Generation Prompt
How to use: Copy the prompt below, fill in the [ ] fields with your project details, paste into an AI assistant. Review the generated output and adjust to match your actual project.
Create a requirements definition and functional requirements for the following project: Project Name: [Enter] Purpose: [Enter] Main features: [List] Main users: [Enter] Output Part 1 — Requirements List: REQ-ID ¦ Category ¦ Name ¦ Detail (shall be able to) ¦ Priority (MoSCoW) ¦ Acceptance Criteria (Given/When/Then) Output Part 2 — Functional Requirements: FUN-ID ¦ Linked REQ-ID ¦ Function Name ¦ Function Detail ¦ Priority ¦ Estimated Effort (person-days, e.g. 2/5/10/20) Include 8-12 requirements and 15-20 functions. RULE: Acceptance Criteria must only describe how to verify the stated requirement. Never introduce new functionality inside AC — add a new REQ row instead.
Always review AI-generated content and verify accuracy before using in your project.

## Use Cases
Use Cases
Guide: UC-ID links to REQ-ID. Format: Actor → Main Flow (numbered steps) → Alternate / Exception Flow → Pre-condition → Post-condition. | [8 empty] | Traceability (→ Matrix tab)
UC-ID | REQ-ID | Actor | Use Case Name | Main Flow | Alt / Exception Flow | Pre-condition | Post-condition | Status
UC-001 | REQ-010 | Procurement Staff | View Consolidated Inventory | 1. Open dashboard 2. See KPIs 3. Filter/search 4. Inspect excess/shortage | Locked file → flagged, run continues | Data loaded | User authenticated on dashboard | Done | → See Traceability Matrix: REQ-001
UC-002 | REQ-006 | Procurement Staff | Review Anomalies | 1. Open 異常検出 2. See new/fixed 3. Inspect High items 4. Fix in source | WARN/FAIL → check layout drift | Scan has run | Customer detail page shown | In Progress | → See Traceability Matrix: REQ-003
UC-003 | REQ-007 | Buyer | Check Overdue POs | 1. Open 発注・価格 2. Sort by overdue days 3. Follow up with supplier | No overdue → empty | 購買計画 parsed | PDF file downloaded to local device | Draft | → See Traceability Matrix: REQ-010
UC-004 | REQ-008 | Buyer | Look Up Price History | 1. Open price section 2. Search SKU 3. See latest price/supplier + history | No history → empty | 購買計画 has prices | [Post] | Not Started
UC-005 | REQ-001 | System (scheduler) | Daily Auto Refresh | 1. Trigger daily 2. Fetch NAS 3. Rebuild all 4. Update dashboard | File locked → skip + flag | NAS access granted

## Business Rules
Business Rules
Guide: Each rule must be testable. Write as: 'The system must...' or 'If [condition] then [action]'. Link to REQ-ID for traceability.
BR-ID | REQ-ID | Rule Name | Rule (The system must... / If...Then...) | Category | Priority | Status | Traceability (→ Matrix tab)
BR-001 | REQ-003 | Excess / Reorder Thresholds | Days-of-stock thresholds are configurable per category (e.g. reorder ≤60d, excess >100d; UDIMM 75d, NotePC 42d). | Validation | Must | Approved | → See Traceability Matrix: REQ-001
BR-002 | REQ-003 | Negative Stock Flag | If stock balance < 0, flag as a data-quality error; never silently copy. | Validation | Must | Approved | → See Traceability Matrix: REQ-001
BR-003 | REQ-004 | Reconciliation Pass | A file passes only when parsed count = expected count and no blocks are dropped. | Process | Must | Approved | → See Traceability Matrix: REQ-003
BR-004 | REQ-007 | Actionable Overdue | Overdue = open order with PO# + supplier whose delivery passed within 180 days. | Process | Should | Approved | → See Traceability Matrix: REQ-004
BR-005 | REQ-009 | Incoming-Excess Trigger | Warn when projected days after inbound exceed the category excess threshold. | Process | Must | Approved | → See Traceability Matrix: REQ-005
BR-006 | REQ-011 | No Source Writes | The system must never write to source or master files. | Process | Must | Approved | → See Traceability Matrix: REQ-011